## Sheet1
Risk number | Risk | Likelihood | impact | Score | Mitigation
Week1.1 | card ID number is larger than 52 or smaller than 1 | 2 | 5 | 10 | There should be a card number error message if the card is initialized out of the range of 1-52
Week1.2 | card suit other than the four suits | 1 | 5 | 5 | Initialized the card with only the four suits./
Week1.3 | Card issued but cannot identify which card it is. | 3 | 1 | 3 | Have a function to print out the name of the card
Week2.1 | There should be exactly 4 players | 1 | 5 | 5 | Give the id for players, but more function will be add to the game class
Week2.2 | Each player should have exactly 13 card, shuffled | 3 | 4 | 12 | Shuffled all the cards in the beginning, and split evenly to the four players.
Week2.3 | The player forget to input their name | 4 | 1 | 4 | Have a function to give random name as default
Week2.4 | Duplicated cards | 1 | 5 | 5 | use a loop and iterate only once to prevent it from happening