## Sheet1
Risk number | Risk | Likelihood | impact | Score | Mitigation | Solved?
Week1.1 | card ID number is larger than 52 or smaller than 1 | 2 | 5 | 10 | There should be a card number error message if the card is initialized out of the range of 1-52 | yes
Week1.2 | card suit other than the four suits | 1 | 5 | 5 | Initialized the card with only the four suits. | yes
Week1.3 | Card issued but cannot identify which card it is. | 3 | 1 | 3 | Have a function to print out the name of the card | yes
Week2.1 | There should be exactly 4 players | 1 | 5 | 5 | Give the id for players, but more function will be add to the game class | yes
Week2.2 | Each player should have exactly 13 card, shuffled | 3 | 4 | 12 | Shuffled all the cards in the beginning, and split evenly to the four players. | yes
Week2.3 | The player forget to input their name | 4 | 1 | 4 | Have a function to give random name as default | yes
Week2.4 | Duplicated cards | 1 | 5 | 5 | use a loop and iterate only once to prevent it from happening | yes
Week2.5 | Other players knows which card is suppressed | 4 | 5 | 20 | Need to create a new random code for each new game for each card, different from the card ID | yes
Week2.6 | Player supress cards when there are still cards available | 4 | 3 | 12 | need to check availability first before allowing player to suppress | Yes
Week3.1 | Player issues card which is not available | 2 | 4 | 8 | check availability first | Yes
Week3.2 | Player issues card which is on board | 2 | 4 | 8 | if a card is onboard, it is not available | Yes
Week3.3 | Player input the card code which doesn't belong to him/her | 4 | 4 | 16 | Use a while loop, if not legal, let the player do it again. | Yes